## Dashboard
WinStar Email Marketing Executive Dashboard 4/24/2018
EMAIL MARKETING WEEKLY TASK LIST
Description | Task |  | Owner(s) | Due Date | Mail Date
(9) May Hotel Reminder | Pending Final creative and List approval |  | Chris, Lisa | 2018-04-24 | 2018-04-24
(2) TWGS Rio Carnival | Pending Lists and final approvals |  | Chris, Lisa | 2018-04-24 | 2018-04-24
May Promotion Highlights | Set to Deploy |  | Lisa | 2018-04-25 | 2018-04-25
(2) Level Up Emails | Pending tests, Lists, Approval |  | Chris, Lisa | 2018-04-24 | 2018-04-30
May Birthday Greeting | Pending Lists and final approvals |  | Chris, Lisa | 2018-04-26 | 2018-04-30
(2) Golf Membership Reminders | Pending tests, Lists, Approval |  | Chris, Lisa | 2018-04-25 | 2018-05-01
Ghosted Patrons Program (3/6/9 mo) | Pending final creative, Tests, Approvals |  | Josh, Chris | 2018-04-24 | 2018-05-01
New Append Data | Checing with IT |  | Angela | 2018-04-24 | 2018-04-30
Welcome Email | Complete, running hourly/daily now |  | Josh, Mark, Lisa | N/A | N/A
Barcoded Email | Awaiting word on new hardware |  | Deb, Chris, Angela | TBD | TBD
Hotel Email Journey | Pending Tony G implementation of FTP drop |  | Tony, Deb, Chris | TBD | TBD
MOST RECENT EMAILS SENT - 4/2018
Description | Date/Time Sent | Emails Sent
180423ONL1_ONEderful | 2018-04-23 15:05 | 161599
180420ENT1 - Jay Leno Passport Offer | 2018-04-20 15:01 | 713
180419CRD4 - Fallout Elite (L1) | 2018-04-19 15:01 | 149
180419CRD3 - Fallout Premier (L2) | 2018-04-19 15:01 | 510
180419CRD2 - Status Premier (L2) | 2018-04-19 15:01 | 229
180419CRD1 - Status Base (WP) | 2018-04-19 15:01 | 24880
180418PRM1 - April Spa Special | 2018-04-18 15:12 | 1300996
180417PRM1 - Apr Non-Responders | 2018-04-17 15:02 | 38698
180416PRM2 - Level Up Elite | 2018-04-16 16:55 | 86
180416PRM1 - Level Up Premier | 2018-04-16 16:55 | 228
180413HTL7 - Apr Hotel S-Th 2-2 Unprotected Redeploy | 2018-04-13 15:02 | 19945
180413HTL5 - Apr Hotel S-F 2-2 Unprotected Redeploy | 2018-04-13 15:02 | 62828

## MostRecentEmailPivot
Sum of Emails Sent
Row Labels | Total
Entmt | 1304355
Golf | 836
Hotel | 262762
Promo | 1372141
Online | 161599
Total | 3101693

## MostRecentEmails
Name | Date/Time Sent | Emails Sent | Category
180423ONL1_ONEderful | 2018-04-23 15:05 | 161599 | Online
180420ENT1 - Jay Leno Passport Offer | 2018-04-20 15:01 | 713 | Promo
180419CRD4 - Fallout Elite (L1) | 2018-04-19 15:01 | 149 | Promo
180419CRD3 - Fallout Premier (L2) | 2018-04-19 15:01 | 510 | Promo
180419CRD2 - Status Premier (L2) | 2018-04-19 15:01 | 229 | Promo
180419CRD1 - Status Base (WP) | 2018-04-19 15:01 | 24880 | Promo
180418PRM1 - April Spa Special | 2018-04-18 15:12 | 1300996 | Promo
180417PRM1 - Apr Non-Responders | 2018-04-17 15:02 | 38698 | Promo
180416PRM2 - Level Up Elite | 2018-04-16 16:55 | 86 | Promo
180416PRM1 - Level Up Premier | 2018-04-16 16:55 | 228 | Promo
180413HTL7 - Apr Hotel S-Th 2-2 Unprotected Redeploy | 2018-04-13 15:02 | 19945 | Hotel
180413HTL5 - Apr Hotel S-F 2-2 Unprotected Redeploy | 2018-04-13 15:02 | 62828 | Hotel
180413HTL4 - Apr Hotel any 2-2 Unprotected V2 Redeploy | 2018-04-13 15:02 | 143974 | Hotel
180413HTL3 - Apr Hotel any 2-4 Unprotected V2 Redeploy | 2018-04-13 15:02 | 26770 | Hotel
180413HTL6 - Apr Hotel S-Th 2-2 Protected Redeploy | 2018-04-13 15:01 | 4224 | Hotel
180413HTL2 - Apr Hotel any 2-2 Protected V2 Redeploy | 2018-04-13 15:01 | 3793 | Hotel
180413HTL1 - Apr Hotel any 2-4 Protected V2 Redeploy | 2018-04-13 15:01 | 1228 | Hotel
180412PRM1 - Pack Your Bags | 2018-04-12 15:01 | 5423 | Promo
180412ENT1 - Jim Jefferies Passport Offer | 2018-04-12 15:01 | 731 | Entmt
180411ENT1 - May Entertainment Highlights | 2018-04-11 15:11 | 1303624 | Entmt
180402GLF2 - April New Elite | 2018-04-04 15:02 | 148 | Golf
180402GLF1 - April New Premier | 2018-04-04 15:01 | 688 | Golf
180402PRM2 - Level Up Elite | 2018-04-02 15:01 | 90 | Promo
180402PRM1 - Level Up Premier | 2018-04-02 15:01 | 139 | Promo
|  | 3101693 | Total

## WeeklyHeadlines
HeadlineID | Description | Task | Owner(s) | Due Date | Mail Date
1 | (9) May Hotel Reminder | Pending Final creative and List approval | Chris, Lisa | 2018-04-24 | 2018-04-24
2 | (2) TWGS Rio Carnival | Pending Lists and final approvals | Chris, Lisa | 2018-04-24 | 2018-04-24
3 | May Promotion Highlights | Set to Deploy | Lisa | 2018-04-25 | 2018-04-25
4 | (2) Level Up Emails | Pending tests, Lists, Approval | Chris, Lisa | 2018-04-24 | 2018-04-30
5 | May Birthday Greeting | Pending Lists and final approvals | Chris, Lisa | 2018-04-26 | 2018-04-30
6 | (2) Golf Membership Reminders | Pending tests, Lists, Approval | Chris, Lisa | 2018-04-25 | 2018-05-01
7 | Ghosted Patrons Program (3/6/9 mo) | Pending final creative, Tests, Approvals | Josh, Chris | 2018-04-24 | 2018-05-01
8 | New Append Data | Checing with IT | Angela | 2018-04-24 | 2018-04-30
9 | Welcome Email | Complete, running hourly/daily now | Josh, Mark, Lisa | N/A | N/A
10 | Barcoded Email | Awaiting word on new hardware | Deb, Chris, Angela | TBD | TBD
11 | Hotel Email Journey | Pending Tony G implementation of FTP drop | Tony, Deb, Chris | TBD | TBD
12

## StrategicDecisionPoints
DecisionID | Description
1 | App and Email Report pull data and send to WS by EOD (1st of each month)
2 | Strategic Program Planning: 2, 3, 5 year plans to include longterm Roadmap development plan.
3 | Review New Architectural Demo (for information architecture primarily)
4 | Finalize Planning for Long-Term MobileEyes Roadmap

## MonthlyInvoice
Month | Year | MonthYearDisplay | Invoice Amount
11 | 2017 | Nov 2017 | 29600
12 | 2017 | Dec 2017 | 30985
1 | 2018 | Jan 2018 | 31820
2 | 2018 | Feb 2018 | 28490
3 | 2018 | Mar 2018 | 33855

## MonthlyHours
Month | Year | MonthYearDesc | Person | Legend | Hours | Percentage Of Total | Total
10 | 2017 | Oct 2017 | Ferrell | Ferrell [22] [25%] | 22 | 25.29% | 87
10 | 2017 | Oct 2017 | Leifeste | Leifeste [53] [61%] | 53 | 60.92% | 87
10 | 2017 | Oct 2017 | Brown | Brown [8] [9%] | 8 | 9.195% | 87
10 | 2017 | Oct 2017 | Depp | Depp [4] [5%] | 4 | 4.598% | 87
10 | 2017 | Oct 2017 | Smith | Smith [0] [0%] | 0 | 0% | 87
10 | 2017 | Oct 2017 | Florez | Florez [0] [0%] | 0 | 0% | 87

## MobileAppReleases
Store | Version | Release Date
Apple iTunes | 2.4.1 | 2017-08-02
Google Play | 2.4.1 | 2017-08-02