## Dashboard
WinStar Email Marketing Executive Dashboard 6/5/2018
EMAIL MARKETING WEEKLY TASK LIST
Description | Task |  | Owner(s) | Due Date | Mail Date
HNG Redeploy | Set for deployment today at 3 |  | Chris, Lisa | 2018-06-05 | 2018-06-05
July Entertainment Highlights | Pending Email Approval, snapshot + approval |  | Chris/Deb, Angela, Lisa | 2018-06-05 | 2018-06-06
ZZ Top Passport Offer | Pending List, snapshot approval |  | Chris/Deb, Angela, Lisa | 2018-06-05 | 2018-06-07
(8) June Hospitality | Pendiing live data approvals, snapshot approvals |  | Chris/Deb, Angela, Lisa | 2018-06-05 | 2018-06-10
(4) Status emails | Pending email approval (content?) , lists, LD approval, snapshot approvals |  | Chris/Deb, Angela, Lisa | 2018-06-05 | 2018-06-12
Gran Via Lobster night | Need Content, and approvals |  | Chris/Deb, Amanda, Angela, Lisa | 2018-06-05 | 2018-06-13
(2) Level Up | Need approval, snapshots |  | Chris/Deb, Angela, Lisa | 2018-06-11 | 2018-06-15
Brett Eldridge Passport Offer | Pending assets, approvals lists, snapshot, approval |  | Chris/Deb, Angela, Lisa | 2018-06-11 | 2018-06-15
Append Update | Timing from IT? |  | Angela, Mark | 2018-06-06 | 2018-06-01
Ghosted Patron Program | How can we help move this forward? |  | Chris, Amanda, Mark | 2018-06-08 | TBD
Barcoded Email | Awaiting word on new hardware - hold on food related details in email |  | Deb, Chris, Angela | TBD | TBD
Hotel Email Journey | Pending Tony G implementation of FTP |  | Tony, Deb, Chris | TBD | TBD
MOST RECENT EMAILS SENT - 5/2018
Description | Date/Time Sent | Emails Sent
180531ONL1 - Summer Action | 2018-06-01 09:18 | 157432
180604ENT3 - Backstreet Boys | 2018-06-04 15:01 | 2921
180604ENT2 - FloridaGeorgia | 2018-06-04 15:01 | 1211
180604ENT1 - AmyShumer | 2018-06-04 15:01 | 239
180604PRM1 - HNG Redeploy | 2018-06-05 | 0

## MostRecentEmailPivot
Sum of Emails Sent
Row Labels | Total
Entmt | 4371
Promo
Online | 157432
Total | 161803

## MostRecentEmails
Name | Date/Time Sent | Emails Sent | Category
180531ONL1 - Summer Action | 2018-06-01 09:18 | 157432 | Online
180604ENT3 - Backstreet Boys | 2018-06-04 15:01 | 2921 | Entmt
180604ENT2 - FloridaGeorgia | 2018-06-04 15:01 | 1211 | Entmt
180604ENT1 - AmyShumer | 2018-06-04 15:01 | 239 | Entmt
180604PRM1 - HNG Redeploy | 2018-06-05 |  | Promo
|  | 161803 | Total

## WeeklyHeadlines
HeadlineID | Description | Task | Owner(s) | Due Date | Mail Date
1 | HNG Redeploy | Set for deployment today at 3 | Chris, Lisa | 2018-06-05 | 2018-06-05
2 | July Entertainment Highlights | Pending Email Approval, snapshot + approval | Chris/Deb, Angela, Lisa | 2018-06-05 | 2018-06-06
3 | ZZ Top Passport Offer | Pending List, snapshot approval | Chris/Deb, Angela, Lisa | 2018-06-05 | 2018-06-07
4 | (8) June Hospitality | Pendiing live data approvals, snapshot approvals | Chris/Deb, Angela, Lisa | 2018-06-05 | 2018-06-10
5 | (4) Status emails | Pending email approval (content?) , lists, LD approval, snapshot approvals | Chris/Deb, Angela, Lisa | 2018-06-05 | 2018-06-12
6 | Gran Via Lobster night | Need Content, and approvals | Chris/Deb, Amanda, Angela, Lisa | 2018-06-05 | 2018-06-13
7 | (2) Level Up | Need approval, snapshots | Chris/Deb, Angela, Lisa | 2018-06-11 | 2018-06-15
8 | Brett Eldridge Passport Offer | Pending assets, approvals lists, snapshot, approval | Chris/Deb, Angela, Lisa | 2018-06-11 | 2018-06-15
9 | Append Update | Timing from IT? | Angela, Mark | 2018-06-06 | 2018-06-01
10 | Ghosted Patron Program | How can we help move this forward? | Chris, Amanda, Mark | 2018-06-08 | TBD
11 | Barcoded Email | Awaiting word on new hardware - hold on food related details in email | Deb, Chris, Angela | TBD | TBD
12 | Hotel Email Journey | Pending Tony G implementation of FTP | Tony, Deb, Chris | TBD | TBD

## StrategicDecisionPoints
DecisionID | Description
1 | App and Email Report pull data and send to WS by EOD (1st of each month)
2 | Strategic Program Planning: 2, 3, 5 year plans to include longterm Roadmap development plan.
3 | Review New Architectural Demo (for information architecture primarily)
4 | Finalize Planning for Long-Term MobileEyes Roadmap

## MonthlyInvoice
Month | Year | MonthYearDisplay | Invoice Amount
1 | 2018 | Feb 2018 | 28490
2 | 2018 | Mar 2018 | 33855
3 | 2018 | Apr 2018 | 35105
4 | 2018 | May 2018 | 39451.25

## MonthlyHours
Month | Year | MonthYearDesc | Person | Legend | Hours | Percentage Of Total | Total
10 | 2017 | Oct 2017 | Ferrell | Ferrell [22] [25%] | 22 | 25.29% | 87
10 | 2017 | Oct 2017 | Leifeste | Leifeste [53] [61%] | 53 | 60.92% | 87
10 | 2017 | Oct 2017 | Brown | Brown [8] [9%] | 8 | 9.195% | 87
10 | 2017 | Oct 2017 | Depp | Depp [4] [5%] | 4 | 4.598% | 87
10 | 2017 | Oct 2017 | Smith | Smith [0] [0%] | 0 | 0% | 87
10 | 2017 | Oct 2017 | Florez | Florez [0] [0%] | 0 | 0% | 87

## MobileAppReleases
Store | Version | Release Date
Apple iTunes | 2.4.1 | 2017-08-02
Google Play | 2.4.1 | 2017-08-02