## Dashboard
WinStar - Mobile App Weekly Executive Dashboard
WEEKLY HEADLINES |  | MOST RECENT MOBILE APP RELEASES
No. | Description | Store | Version | Release Date
1 | App maintenance: Android Client R3 review - ready to schedule | Apple iTunes | 2.4.4 | 2017-12-04
2 | Discuss App Sunset plan/next steps - met with Jamie; follow-up questions | Google Play | 2.4.1 | 2017-08-02
3 | Bonus play issue: Found a javascript error, could fix issue; push both Android and Iphone version next
4 | Dining Barcode Offers: on hold (awaiting addt'l details for dev/timing) - see email update
STRATEGIC DECISION POINTS
No. | Description
1 | App and Email Report pull data and send to WS by EOD (1st of each month)
2
3
4
MONTHLY INVOICE TRENDS

## WeeklyHeadlines
HeadlineID | Description
1 | App maintenance: Android Client R3 review - ready to schedule
2 | Discuss App Sunset plan/next steps - met with Jamie; follow-up questions
3 | Bonus play issue: Found a javascript error, could fix issue; push both Android and Iphone version next
4 | Dining Barcode Offers: on hold (awaiting addt'l details for dev/timing) - see email update

## StrategicDecisionPoints
DecisionID | Description
1 | App and Email Report pull data and send to WS by EOD (1st of each month)
2
3
4

## MonthlyInvoice
Month | Year | MonthYearDisplay | Invoice Amount
2 | 2018 | Feb 2018 | 27935
3 | 2018 | Mar 2018 | 7770
4 | 2018 | Apr 2018 | 11100
5 | 2018 | May 2018 | 17390

## MonthlyHours
Month | Year | MonthYearDesc | Person | Legend | Hours | Percentage Of Total | Total
4 | 2018 | Apr 2018 | Ferrell | Ferrell [4] [47%] | 4 | 47.06% | 8.5
4 | 2018 | Apr 2018 | Leifeste | Leifeste [3] [35%] | 3 | 35.29% | 8.5
4 | 2018 | Apr 2018 | Brown | Brown [0.5] [6%] | 0.5 | 5.882% | 8.5
4 | 2018 | Apr 2018 | Townsend | Townsend [1] [12%] | 1 | 11.76% | 8.5
4 | 2018 | Apr 2018 | Smith | Smith [0] [0%] | 0 | 0% | 8.5

## MobileAppReleases
Store | Version | Release Date
Apple iTunes | 2.4.4 | 2017-12-04
Google Play | 2.4.1 | 2017-08-02